# Jira + Xray Sprint Workflow Guide

### Building “BS – Build System”: from board setup to a closed, tested sprint

This guide walks through a complete Scrum + Xray workflow in Jira: setting up a board, adding Xray testing issue types, building out a backlog (Epic → Story → Test → Precondition), running a sprint, executing tests, handling a bug, and closing out with demo/approval/done.

Scope strategy used throughout: hybrid — the Story, its Tests, and its Preconditions all enter the sprint together on day 1; the Test Execution is created later once the Story reaches Testing.

## Phase 1: Board Setup

### Step 1 — Create Jira Scrum Board

- Navigate to Jira Spaces and, in the right side panel under “Templates available,” click + Scrum.

- Choose Scrum — the “Deliver work in short time blocks” board type.

- Select Software development, select Scrum again, then Use template. Name your space Build System with key BS.

- Very important: how your space is managed must be set to Company-Managed. Ignore the “Share settings with an existing space” option.

- Click Next — ignore “Let’s set up your space,” click Next again. Ignore adding users (you’ll add them properly in the next step). Click Next and accept the Confluence part — Confluence Whiteboards are great for planning, requirements gathering, and sprint retrospectives. Jira creates the project, board, and Confluence wiki together.

- Go to Board settings → Columns and make sure the following columns exist (add any missing ones with the + on the right side): Sprint Backlog, Blocked, In Progress, Testing, Demo, Approval, Done. Drag columns into place with your mouse as needed.

- In the menu above the board, make sure Backlog sits before Active Sprints — drag them into place if not. Remember: the Product Owner’s backlog work happens before sprinting, so the layout should read left to right in that order.

- Important: bookmark your new board in your internet browser.

Tip: The project key (BS) cannot be changed once issues exist. Keep it short — 2–4 characters.

### Step 2 — Add Users to the Board

- Find the small > arrow at the top left and use it to open the left-hand panel with Project (now called Space) Settings. Find your project name, click the 3 dots to the right of it, and — ignoring “Add people” — go to Space Settings in the dropdown. You should see People there. Use this setting to add every user who will use your board, along with their role.

- Assign roles: Administrator, Developer, or Viewer.

- For Xray, testers need at least the Developer role to create and execute tests.

- Click Save.

Tip: Board-level roles differ from project-level roles. A Developer on the board can move cards; only Admins can change board settings.

### Step 3 — Add Xray Issue Types to Board

- Make sure the left panel is open (use the > button top left).

- Go to … More → APPS → Xray → Getting Started.

- In the top left of the middle panel, use Quick Setup → Configure Project. In the dropdown, find and select your new project, then click Configure.

- You’ll see a panel showing the new Testing issue types, each with an ✗ next to it. Above that panel, find Add Xray Issue Types and click it — the ✗s turn into ticks, confirming the Xray issue types have been added to Jira.

- Use your browser bookmark to go back to your board view. Xray issue types will now appear in the + Create dropdown at the top of the page, above your board.

Tip: Xray issues (Test, Precondition, Test Execution) typically carry 0 story points — they track testing scope, not delivery effort.

## Phase 2: Backlog

### Step 4 — Create Epic: Build System

Issue type: Epic · Burndown impact: none — Epics are containers, not sprint items · Column: Backlog (Epics panel) · Points: 0

- Go to Backlog view via the menu above your sprint board.

- In the Epic dropdown above the Sprint and Backlog panels (center of screen), enable Epics at the bottom of the dropdown. An Epics panel opens on the left — click + Create epic.

- Name it Build System.

- Set a colour and, optionally, a start/due date.

- Click Create.

Tip: Epics span multiple sprints and group related User Stories. They live in the Epics panel, not as cards on the board.

### Step 5 — Create User Story

Issue type: Story · Burndown impact: none yet — story is in backlog, not a sprint · Column: Backlog · Points: 0

- In Backlog, in the Epic dropdown on the left panel, click Create Work Item.

- Set issue type to Story.

- Summary: Create User Registration and Login System.

- Add details in the Description field. You can format with bold, italic, bullet points, checkboxes, etc. Jira also lets you insert a date shortcut with /d or a + symbol.

- You’ll probably need a custom field called Acceptance Criteria (setup may differ depending on your instance):

  - Click > top left to open the left panel, click … next to your project name, then Space Settings → Work Items → Layout. These work types show the fields defined in something like “XD: Scrum Default Issue Screen.”

  - Click the name, scroll to the bottom, choose Select Field, and add Acceptance Criteria.

  - Opening your User Story should now show Acceptance Criteria underneath Description. If you don’t have the rights to do this, your Jira Administrator can set it up for you.

- Link it to the Build System epic using the Parent field.

- Click Create.

- Note that the Epic now shows 1 User Story associated with it, at 0% complete. Viewing the Epic’s details is a good place to track delivery progress — e.g. with 20 User Stories you’d track toward 100% completed. The Backlog also now shows the User Story.

Tip: Write the story in the Description field using the format: “As a [user] I want to [action] so that [benefit]” for clarity.

### Step 6 — Add Story Points to User Story

Issue type: Story · Burndown impact: points set — ready to contribute to sprint burndown · Column: Backlog · Points: 8

- Open issue BS-2 by clicking it in the backlog.

- Find the Story points field (right panel).

- Enter 8 and click outside the field to save.

- The estimate now shows on the backlog card.

Tip: Only the User Story carries points. Tests, Preconditions, and Test Executions should be 0 points — otherwise your velocity will be inflated and your burndown misleading.

### Step 7 — Create Test Issue

Issue type: Test · Burndown impact: 0 pts — Xray tests carry no story points · Column: Backlog · Points: 0

- In Backlog, click + Create issue → type Test.

- Summary: Verify user login with valid credentials.

- In the Test Details tab, set Test Type to Manual.

- Add Test Steps:

  - User navigates to login page → Expected: Login form is displayed

  - User enters valid username → Expected: Username field accepts input

  - User enters valid password → Expected: Password field accepts input

  - User clicks Login → Expected: User is redirected to dashboard

- Click Create.

Tip: Write Tests during sprint planning or day 1. This is your “test-first” practice — the test defines what “done” means for the story.

### Step 8 — Create Precondition

Issue type: Precondition · Burndown impact: 0 pts — Preconditions are setup conditions, not effort · Column: Backlog · Points: 0

- Click + Create issue → type Precondition.

- Summary: User needs a system to test in.

- In the Condition field, describe: “A test environment must be running with a seeded database.”

- Click Create.

- Open Test issue BS-3 → scroll to the Preconditions panel → click + → link BS-4.

Tip: Preconditions are reusable — one Precondition can be linked to many Tests. Think of them as shared “given” conditions across your test suite.

### Step 9 — Link Test to User Story

Issue type: Story · Burndown impact: none — linking creates traceability only · Column: Backlog · Points: 0

- Open User Story BS-2.

- Click Link (in the issue details toolbar).

- Link type: is tested by.

- Search for and select BS-3 (the Test).

- Click Save.

- Alternatively, open BS-3 → Tests panel → + Add to Story → select BS-2.

Tip: The “is tested by” link type creates bidirectional traceability: from the Story you can see all its Tests; from the Test you can see all Stories it covers.

## Phase 3: Sprint Planning / Sprint Active

### Step 10 — Create Sprint

Burndown impact: sprint created — burndown starts at 0 until issues are moved in

- In Backlog, scroll to the top and click Create sprint.

- Click the … menu on the sprint → Edit sprint.

- Set Sprint name: BS Sprint 1.

- Set Start date and End date (e.g. a 2-week sprint).

- Set Sprint goal: “Deliver user registration and login with passing tests.”

- Click Update.

- More detail: you’ll create just one User Story for this Epic, worth 8 story points. Add “8” to the right of the User Story in Backlog, then — assuming you have a user allocated to do the work — drag the User Story up into the first sprint, click Start sprint, and give it 1 week. Then move to Active Sprints using the button at the top of the board, and drag your User Story into In Progress.

- At the top menu, next to Reporting Center and Testing Board (both Xray features), click the + button and add Reports to the navigation.

- When the reports dashboard appears, click More Reports and find Burndown Chart. You should see the burndown guideline — a line moving from top left to bottom right. As you complete stories, actuals appear next to the guideline showing progress. With only 1 User Story, the guideline may not display correctly on day 1; it becomes clearer after day 1 and with more stories.

Tip: The sprint goal keeps the team focused. It should describe the value delivered, not just a list of tickets.

### Step 11 — Move Issues to Sprint

Burndown impact: 8 pts added to sprint — burndown chart now shows 8 pts remaining · Column: Sprint Backlog · Points: 8

- In Backlog, right-click BS-2 (Story) → Move to sprint → BS Sprint 1.

- Right-click BS-3 (Test) → Move to sprint → BS Sprint 1.

- Right-click BS-4 (Precondition) → Move to sprint → BS Sprint 1.

- Click Start sprint — all three issues now appear in Sprint Backlog.

- Burndown = 8 pts (only the Story has points — Tests and Preconditions = 0).

Tip: This is the “hybrid” approach: Story + Tests + Preconditions enter the sprint together on day 1. The Test Execution is created later, once the Story enters Testing. Scope changes once — predictably.

### Step 12 — Move Story to In Progress

Issue type: Story · Burndown impact: 8 pts remaining — no change until story is Done · Column: In Progress · Points: 8

- On the Sprint board, drag BS-2 from Sprint Backlog to In Progress.

- Or open the issue and change Status to In Progress.

- Assign a developer to the story.

- The burndown does not change — remaining work is still 8 pts.

Tip: The burndown only drops when issues move to Done. Moving to In Progress just tells the team “someone is working on this.”

### Step 13 — Move Story to Testing

Issue type: Story · Burndown impact: 8 pts remaining — story built, awaiting testing · Column: Testing · Points: 8

- Development is complete. Drag BS-2 to Testing.

- “Testing” here means the feature is deployed to a test/staging environment, ready for QA.

- This is the trigger to create the Test Execution.

- The tester is notified that the story is ready for testing.

Tip: Moving the story to Testing signals the dev work is done. The tester now takes ownership and creates a Test Execution to run the Xray tests.

## Phase 4: Testing / Bug Handling

### Step 14 — Create Test Execution

Issue type: Test Execution · Burndown impact: 8 pts — Test Execution = 0 pts, no burndown change · Column: Testing · Points: 0

- Click + Create issue → type Test Execution.

- Summary: BS Sprint 1 — Login Test Execution.

- In the Test Execution panel, click + Add tests → add BS-3.

- Set Assignee to the tester.

- Click Create.

- Move the Test Execution into BS Sprint 1 and drag it to Testing.

Tip: A Test Execution is the “run” of your tests at a specific point in time. You can run the same Tests multiple times across different Test Executions (e.g. regression cycles).

### Step 15 — Run Test Execution

Issue type: Test Execution · Burndown impact: 8 pts remaining — tests running · Column: Testing · Points: 0

- Open BS-5 (Test Execution).

- Click Execute — the Xray Test Player opens.

- For each test step, click Pass or Fail.

- If a step Fails: click Create Bug — Xray auto-links the bug to this execution.

- Add evidence: screenshots, comments per step.

- When all steps are marked, the execution status updates automatically (Passed / Failed).

Tip: Xray records who ran the test, when, and the result of each step. This creates a full audit trail for compliance and regression analysis.

### Step 16 — Create Bug from Failed Step

Issue type: Bug · Burndown impact: Bug = 0 pts (unplanned); Story still 8 pts remaining · Column: In Progress · Points: 0

- During execution of BS-5, Step 4 (“User clicks Login”) fails.

- Click Create Bug in the Xray test player.

- Xray pre-fills: summary, links to Test Execution, attaches step evidence.

- The Bug (BS-6) appears on the board — move it to In Progress.

- Developer fixes the bug.

- Bug moves to Testing for retest.

Tip: Bugs created from Test Executions automatically have full traceability: Bug → Test Step → Test Execution → Test → User Story. No manual linking needed.

### Step 17 — Retest & Close Test Execution

Issue type: Test Execution · Burndown impact: 8 pts remaining — story not Done yet · Column: Testing · Points: 0

- Bug BS-6 is fixed and moved to Testing.

- Tester opens BS-5 → re-executes the failed step.

- Step now Passes — all steps green.

- Test Execution status changes to Passed.

- Move Bug BS-6 to Done.

- Close the Test Execution — move BS-5 to Done.

Tip: You can re-run individual failed steps without re-running the whole execution. Xray tracks the retest as a new execution run within the same Test Execution issue.

## Phase 5: Completion

### Step 18 — Demo to Product Owner

Issue type: Story · Burndown impact: 8 pts remaining — awaiting PO sign-off · Column: Demo · Points: 8

- All tests passed. Move BS-2 (Story) to Demo.

- Move BS-6 (Bug) to Done.

- Present the feature to the Product Owner in the sprint review.

- PO validates against the acceptance criteria.

- PO satisfied → move story to Approval.

Tip: The Demo column is where you show working software. Keep it focused on the sprint goal — show what was built, not how it was built.

### Step 19 — Approval by Product Owner

Issue type: Story · Burndown impact: 8 pts remaining — awaiting formal PO approval · Column: Approval · Points: 8

- PO satisfied with demo → move BS-2 to Approval.

- PO formally signs off against the Definition of Done.

- Any final feedback is captured as new backlog items — not by reopening this story.

- PO approves → story is ready to move to Done.

Tip: Separating Demo from Approval gives the PO time to review without pressure. Approval is the formal gate; Demo is the conversation.

### Step 20 — Move to Done & Close Sprint

Burndown impact: 0 pts remaining — burndown complete! 🎉 · Column: Done · Points: 0

- PO approves → drag BS-2 (Story) to Done.

- Burndown chart drops to 0 — sprint goal achieved.

- Move remaining items (BS-3, BS-4) to Done.

- In Backlog, click Complete sprint on BS Sprint 1.

- Jira generates a Sprint Report showing velocity and completed work.

- Hold a Sprint Retrospective to review what went well and what to improve.

Tip: Velocity = story points completed per sprint. Over 3–5 sprints, your velocity stabilises and becomes a reliable planning tool for future sprints.

## Summary: Issue Keys Created

| Key | Type | Summary | Points |
| --- | --- | --- | --- |
| BS-1 | Epic | Build System | — |
| BS-2 | Story | Create User Registration and Login System | 8 |
| BS-3 | Test | Verify user login with valid credentials | 0 |
| BS-4 | Precondition | User needs a system to test in | 0 |
| BS-5 | Test Execution | BS Sprint 1 — Login Test Execution | 0 |
| BS-6 | Bug | Login redirect fails after valid credentials | 0 |

Final state: All 6 issues in Done. Sprint closed. Burndown at 0. Sprint Report generated.